## administration
Name (pls rename) | Task types | Status | Instructions:
Gunnraj Dhaliwal | UML diagram | TODO | Please rename the file and copy the shared link to your repository. Due to academic integrity, failure to do so may result in 0 mark.
Behnam Mozafari | Design rationale | IN PROGRESS | Put your team members' name in "Name" column (A2-A5)
Josh Ryan | Discussion | DONE | Please go to another tab below (Assignment 1, 2 or 3)
EVERYONE | Brainstorm | INCOMPLETE | As a team, discuss and list on what tasks that need to be done along with its type.
| Code comment |  | Ideally you'll assign yourself to a task. However, you're welcome to assign a task to someone if everyone agrees on that.
| Code review |  | While working on a task, please change the status from "TODO" to "IN PROGRESS" to inform your team that you are working on that task.
| Code |  | Once you're done, log the date you've completed the task. Feel free to add extra notes if that help your team understands what've you done with the task. Ideally you'll write a brief reflection on the completed task.
| Sequence Diagram |  | Ideally a task need to be atomic (only one thing), so it shouldn't be shared/done by two people except as a whole "Team discussion".
In a case that you're unable to complete the task and it will be taking over by someone else, set the status to INCOMPLETE, and create a fresh new log with new planning date and contributor's name.
Feel free to add more contribution types if you think they are insufficient
Your markers may have a look at the Version History to make decisions if there are imbalance of contributions. So, please notify your lab demonstrators if that's the case.

## Assignment 1
Task/Contribution(~30 words) | Contribution type | Planning Date | Contributor | Status | Actual Completion Date | Extra notes
First Meeting Discussion | Discussion | 2023-03-25 | EVERYONE | DONE | 2023-03-25 | We had a 1 hour meeting to read the assignment specifications together and distributed work equally among team members. The team agreed to have the next meeting on 1/04/2023. Using the recommended task split given by the brief, Behnam will act as Team member 1, Gunnraj will act as team member 2 and Josh will act as team member 3
REQ 1 - Environments | UML diagram | 2023-03-25 | Gunnraj Dhaliwal | DONE | 2023-04-12
REQ 1 - Enemies | UML diagram | 2023-03-25 | Behnam Mozafari | DONE | 2023-04-12
REQ 4 - Classes (Combat Archetypes) | UML diagram | 2023-03-25 | Josh Ryan | DONE | 2023-04-11
Second Meeting Discussion | Discussion | 2023-04-02 | EVERYONE | DONE | 2023-04-10 | 1 hour catchup meeting to discuss progress and next tasks, Behnam will work on REQ 5, Gunnraj will do REQ 3 (game reset), Josh will do REQ 3 (Flask, site of lost grace and runes).
REQ 3-Flask, site of lost grace and runes | UML diagram | 2023-03-31 | Josh Ryan | DONE | 2023-04-12
REQ 4 - Classes (Combat Archetypes) | Design rationale | 2023-03-25 | Josh Ryan | DONE | 2023-04-14
REQ 3-Flask, site of lost grace and runes | Design rationale | 2023-03-31 | Josh Ryan | DONE | 2023-04-14
REQ 5 | UML diagram | 2023-03-25 | Behnam Mozafari | DONE | 2023-04-12
Third Meeting Discussion | Discussion | 2023-04-08 | EVERYONE | Done | 2023-04-08 | 1 hour meeting to discuss progress, and to discuss extension and then determine if everyone will be able to complete tasks by end of mid semester break. Questions about tasks were asked and answered by team mates
REQ 1 - Enemies | Design rationale | 2023-03-25 | Behnam Mozafari | DONE | 2023-04-15
REQ 5 | Design rationale | 2023-03-27 | Behnam Mozafari | DONE | 2023-04-15
REQ 2 - Enemies | Design rationale | 2023-03-23 | Behnam Mozafari | DONE | 2023-04-15
REQ 2 - Enemies | UML diagram | 2023-03-23 | Behnam Mozafari | DONE | 2023-04-15
REQ 2 - Trader | UML diagram | 2023-03-24 | Gunnraj Dhaliwal | DONE | 2023-04-12
REQ 1 - Environments | Design rationale | 2023-03-25 | Gunnraj Dhaliwal | DONE | 2023-04-15
REQ 2 - Trader | Design rationale | 2023-03-26 | Gunnraj Dhaliwal | DONE | 2023-04-15
Final Assignment Discussion | Discussion | 2023-04-14 | EVERYONE | DONE | 2023-04-15 | 3 hour meeting that aimed to ensure that all tasks had been completed and to provide final feedback/solve misunderstandings before fixing an issues resulting from merging the different requirements.

## Assignment 2
Task/Contribution(~30 words) | Contribution type | Planning Date | Contributor | Status | Actual Completion Date | Extra notes
First meeting discussion for A2 | Discussion | 2023-04-18 | EVERYONE | DONE | 2023-04-18 | Decided for each person to start coding the same parts they had done for A1, planned next meeting for 23/04/2023.
- each environment implements new interface EnemyGroundSpawn as they all use same method - created dummy enemy actor classes for environment types to act as a placeholder - added new method in RandomNumberGenerator - changed RandomNumberGenerator.java name to Utils.java - added Merchant class along with BuyAction and SellAction (scaffolds only) | Code | 2023-04-18 | Gunnraj Dhaliwal | DONE | 2023-04-29
Created Enemy Abstract Class, changed LoneWolf Class to extend it (req 1) | Code | 2023-04-18 | Behnam Mozafari | DONE | 2023-04-29
Added archetype interface | Code | 2023-04-18 | Josh Ryan | DONE | 2023-04-18
Added player archetype classes and added archetype as attribute of player (req 4) | Code | 2023-04-18 | Josh Ryan | DONE | 2023-05-02
Added Great Knife and quickstep action (req 4) | Code | 2023-04-18 | Josh Ryan | DONE | 2023-05-28
Added Uchigatana and unsheathe action (req 4) | Code | 2023-04-18 | Josh Ryan | DONE | 2023-05-28
Added capability for player to select class before game start (req 4) | Code | 2023-04-18 | Josh Ryan | DONE | 2023-05-28
Added HealConsumable interface (req 3) | Code | 2023-04-18 | Josh Ryan | DONE | 2023-05-02
Added flask item (req 3) | Code | 2023-04-18 | Josh Ryan | DONE | 2023-05-02
Added heal action (req 3) | Code | 2023-04-18 | Josh Ryan | DONE | 2023-05-02
- added initial instantiation of ResetManager in Application class, as well as stroring the player's initial spawn location in ResetManager - added Util class isLocationLeftOrRight method functionality - this required Util class to be used within Application - created merchant class that should be fully complete - BuyAction and SellAction are mostly complete: requires RuneManager to be completed | Code | 2023-04-18 | Gunnraj Dhaliwal | DONE | 2023-04-22
- created RuneManager class skeleton to handle rune trading - added register and remove resettable methods in ResetManager - added last spawn position into player instead of ResetManager | Code | 2023-04-18 | Gunnraj Dhaliwal | DONE | 2023-04-22
Created HeavySkeletalSwordsman Class | Code | 2023-04-18 | Behnam Mozafari | DONE | 2023-04-22
Created GiantCrab Class | Code | 2023-04-18 | Behnam Mozafari | DONE | 2023-04-22
Created Grossmesser Weapon | Code | 2023-04-18 | Behnam Mozafari | DONE | 2023-04-22
Created Slam Weapon | Code | 2023-04-18 | Behnam Mozafari | DONE | 2023-04-22
Second meeting discussion for assignment 2 | Discussion | 2023-04-21 | EVERYONE | DONE | 2023-04-23 | 1 hour meeting to discuss current progress on code and merge progress into main branch. Also set date and time for next meeting.
Created sequence diagram for Req 4 | UML diagram | 2023-04-22 | Josh Ryan | DONE | 2023-05-01
Added drop runes method to RuneManager class | Code | 2023-04-27 | Josh Ryan | DONE | 2023-04-27
Created sequence diagram for Req 3 | UML diagram | 2023-04-24 | Josh Ryan | DONE | 2023-05-02
Remade UML diagram for Req 4 |  | 2023-04-25 | Josh Ryan | DONE | 2023-05-01
Remade UML diagram for Req 3 (Flask and Site of Lost grace) | UML diagram | 2023-04-23 | Josh Ryan | DONE | 2023-05-02
Remade UML diagram for Req 3 (Reset) | UML diagram |  | Gunnraj Dhaliwal | DONE
Created site of lost grace (req 3) | Code | 2023-04-20 | Josh Ryan | DONE | 2023-05-02
Created Classes from Req 5 | Code | 2023-04-23 | Behnam Mozafari | DONE | 2023-04-28
Created EnemyAttackBehaviour | Code | 2023-04-23 | Behnam Mozafari | DONE | 2023-04-29
Created AOEAttackAction | Code | 2023-04-23 | Behnam Mozafari | DONE | 2023-04-29
Created BuyAction, SellAction, Runes and RuneManager to handle rune interractions | Code | 2023-04-23 | Gunnraj Dhaliwal | DONE | 2023-04-30
Created New Ground types and Interface for spawning, implemented spawn logic for enemies and updated Utils so that map parity can be determined | Code | 2023-04-23 | Gunnraj Dhaliwal | DONE | 2023-04-30
Added reset functionality, and respawn functionality. Updated SiteOfGraceAction and DeathAction, created playerManager to facilitate this and added functionlaity to Player to handle dropping of Runes | Code | 2023-04-23 | Gunnraj Dhaliwal | DONE | 2023-04-30
Updated Req 1 UML (Enemy Spawning and Grounds) | UML diagram | 2023-04-23 | Gunnraj Dhaliwal | DONE | 2023-04-29
Updated Req 2 UML (Trading, DeathAction) | UML diagram | 2023-04-23 | Gunnraj Dhaliwal | DONE | 2023-04-29
Updated Req 3 UML (Resetting) | UML diagram | 2023-04-24 | Gunnraj Dhaliwal | DONE | 2023-04-29
Created Req1 Sequence Diagram | Sequence Diagram | 2023-04-25 | Gunnraj Dhaliwal | DONE | 2023-04-29
Created Req2 Sequence Diagram | Sequence Diagram | 2023-04-25 | Gunnraj Dhaliwal | DONE | 2023-04-29
Updated Design rationale for req1,2,3 | Design rationale | 2023-04-25 | Gunnraj Dhaliwal | DONE | 2023-04-30
Third meeting discussion for assignment 2 | Discussion | 2023-04-27 | EVERYONE | DONE | 2023-04-27 | 40 minute meeting to discuss progress on code, split up sequence diagrams, Also set date and time for next meeting.
Updated Req1 UML | UML diagram | 2023-04-27 | Behnam Mozafari | DONE | 2023-05-01
Updated Req2 UML | UML diagram | 2023-04-27 | Behnam Mozafari | DONE | 2023-05-01
Updated Req5 UML | UML diagram | 2023-04-27 | Behnam Mozafari | DONE | 2023-05-01
Completed Req 5 sequence diagram | Sequence Diagram | 2023-04-27 | Behnam Mozafari | DONE | 2023-05-01
Fourth meeting discussion for assignment 2 | Discussion | 2023-04-29 | EVERYONE | DONE | 2023-04-29 | 1 hour meeting to discuss progress on code, merge progress into main branch, and also set date and time for next meeting.
Updated Design rationale for req1,2,5 | Design rationale | 2023-04-29 | Behnam Mozafari | DONE | 2023-05-03
Final meeting discussion for assignment 2 | Discussion | 2023-05-01 | EVERYONE | DONE | 2023-05-03 | 1 hour meeting to finish any remaining documentation and submit the assignment.

## Assignment 3
Task/Contribution(~30 words) | Contribution type | Planning Date | Contributor | Status | Actual Completion Date | Extra notes
First meeting discussion for A3 | Discussion | 2023-05-09 | EVERYONE | DONE | 2023-05-09 | Decided the following split up: Behnam: Req1 - door, Req2 - Enemies, Gunnraj: Req 1,2 grounds and Req 3 - trading and Josh: Req 4, Everyone: Req 5. Also decided to fix up A2 from feedback: everyone will do their own parts from A2
Refactored all enemies to use abstract classes for each enemy type | Code | 2023-05-09 | Behnam Mozafari | DONE | 2023-05-13
Created StormveilEnemy abstract class, Dogs and Godrick Soldiers classes | Code | 2023-05-09 | Behnam Mozafari | DONE | 2023-05-15
Fixed Follow Behaviour | Code | 2023-05-09 | Behnam Mozafari | DONE | 2023-05-16
Fixed PileOfBones to spawn the same instance of skeleton enemy | Code | 2023-05-09 | Behnam Mozafari | DONE | 2023-05-16
Refactored AOEAttackAction to use AttackAction | Code | 2023-05-09 | Behnam Mozafari | DONE | 2023-05-16
Refactored Enemy abstract class to Combatant to allow for ally to inherit | Code | 2023-05-09 | Josh Ryan | DONE | 2023-05-15
Created PlayerLike abstract class to be inherited by Ally/Invader | Code | 2023-05-09 | Josh Ryan | DONE | 2023-05-16
Created Ally/Invader classes | Code | 2023-05-09 | Josh Ryan | DONE | 2023-05-16
Created SummonSign ground class | Code | 2023-05-09 | Josh Ryan | DONE | 2023-05-17
Created SummonSignAction class | Code | 2023-05-09 | Josh Ryan | DONE | 2023-05-17
Refactored Trading implentation to allow for a greater range of trades | Code | 2023-05-09 | Gunnraj Dhaliwal | DONE | 2023-05-15
Refactored Consumables so that they're consistent | Code | 2023-05-09 | Gunnraj Dhaliwal | DONE | 2023-05-18
Added Cliff and Other Ground Types | Code | 2023-05-09 | Gunnraj Dhaliwal | DONE | 2023-05-15
Added Golden Rune | Code | 2023-05-09 | Gunnraj Dhaliwal | DONE | 2023-05-19
Added Enia and Rememberances | Code | 2023-05-09 | Gunnraj Dhaliwal | DONE | 2023-05-17
Second meeting discussion for A3 | Discussion | 2023-05-09 | EVERYONE | DONE | 2023-05-16 | Decided on doing New weapons with status effects for req 5, submitted google sheet, split up req5
Created GoldenFogDoor and TeleportAction | Code | 2023-05-16 | Behnam Mozafari | DONE | 2023-05-19
Added new maps | Code | 2023-05-16 | Behnam Mozafari | DONE | 2023-05-19
Added weapons for creative requirement | Code | 2023-05-16 | Josh Ryan | DONE | 2023-05-19
Added reset capability for allies/invaders | Code | 2023-05-16 | Josh Ryan | DONE | 2023-05-19
Updated A2 Req 2 UML | UML diagram | 2023-05-16 | Gunnraj Dhaliwal | DONE | 2023-05-19
Updated A2 Req 3 UML | UML diagram | 2023-05-16 | Gunnraj Dhaliwal | DONE | 2023-05-19
Added A3 Req 3 UML | UML diagram | 2023-05-16 | Gunnraj Dhaliwal | DONE | 2023-05-19
Third meeting discussion for A3 | Discussion | 2023-05-16 | EVERYONE | DONE | 2023-05-19 | Caught up on progress, fixed bugs, created statusEffect abstract class together, fixed merge conflicts
Created Statuses | Code | 2023-05-19 | Behnam Mozafari | DONE | 2023-05-20
Added status functionality to combatants and player | Code | 2023-05-19 | Behnam Mozafari | DONE | 2023-05-20
Updating A2 UML | UML diagram | 2023-05-19 | Behnam Mozafari | DONE | 2023-05-21
Creating A3 UML Req 1 & 2 | UML diagram | 2023-05-19 | Behnam Mozafari | DONE | 2023-05-21
Updated A2 Req 4 UML | UML diagram | 2023-05-16 | Josh Ryan | DONE | 2023-05-20
Created A3 Req 4 UML | UML diagram | 2023-05-16 | Josh Ryan | DONE | 2023-05-20
Created A3 Req 5 UML | UML diagram | 2023-05-16 | Josh Ryan | DONE | 2023-05-20
Added changes to A2 Req 4 to design rationale | Design rationale | 2023-05-16 | Josh Ryan | DONE | 2023-05-20
Added design rationale for A3 Req 4 | Design rationale | 2023-05-16 | Josh Ryan | DONE | 2023-05-20
Added design rationale for A3 Req 5 | Design rationale | 2023-05-16 | Josh Ryan | DONE | 2023-05-20
Changed to A3 Req1 and Req2 UML | UML diagram | 2023-05-16 | Gunnraj Dhaliwal | DONE | 2023-05-20
Added to design rationale for changes to A2 | Design rationale | 2023-05-16 | Gunnraj Dhaliwal | DONE | 2023-05-20
Added to design rationale for changes to A3 Req 2+3 | Design rationale | 2023-05-16 | Gunnraj Dhaliwal | DONE | 2023-05-20
Final meeting to submit A3 | Discussion | 2023-05-20 | EVERYONE | DONE | 2023-05-21 | Submitted assignment 3